## Slide 1
25G Mentor-mentee
  Training plan (MAY/2017 – MAY/2019)
22/JUN/2017
Mentor : Phong Huynh (1349)
Mentee: Pham Thanh (2001)
Renesas Electronics Corporation
Renesas design vietnam co., ltd
STS2/TD3

## Slide 2: Agenda
Traning Target Page 03
Current Status and Target Page 04
Gap analysis and Solution Page 06
Training Plan Page 11

## Slide 3: Training Target
Target: Engineer for test up to level 2 by Apr 2019
Can do Code Generator project task which has a certain difficult degree without help from Seniors/Leaders
Role | Skill | Skill Target |  | Target
Engineer for Test | Test environment construction | Have knowledge of the development environment (compiler, debugger), target environment (OS, middleware, applications, etc.), conduct test and evaluations. |  | 2
 | Test item extraction | Extract test items from various specifications and design specifications. | Round up and integrate and extracted test items into test specifications. | 2
 | Text execution | Conduct test according to the test specifications. | Round up the results and make a report. | 2
 | Failure analysis | Locate the cause of any trouble and make analysis of its influences and other side effects. | Take countermeasures against similar problem. | 2
 | Communication | Can report/explain the issue to teammate or customer | Can report work status in team | 2
 | Management | Can schedule work and follow the schedule strictly | Can manage problem for any technical issues | 2
 | English | Achieve TOEIC 700 |  | 2

## Slide 4: Current status
Role | Skill | Current Status
Engineer for Test | Test environment construction | Can setup environment following guideline of mentor or documents.
 | Test item extraction | Have not create any test spec yet.
 | Text execution | Can execute test items for simple modules.
 | Failure analysis | Can analyze and fix simple failure.
 | Communication | Can report/explain the issue but unclear.
 | Management | Can schedule but not efficiency.
 | English | Do not have any English certification.

## Slide 5: Gap analysis and solution (1/3)
Skill | Gap | Action Item |  | Milestone
 |  | Mentee | Mentor | 
Test Environment Construction | Lack of experience in setting up software environment . Lack of knowledge in software architecture | Set up software testing environment following mentor’s guideline from easy to difficult. Self investigate knowledge in software system architecture with mentor’s support. | Provide materials, instructions. Confirm mentee’s understanding, give feedback. | Jun 2017
Test Item Extraction | Lack of knowledge in understanding the CG architecture. Lack of experience in create new test item and test specification. | Read design specifications carefully, note and make a confirm with mentor to make more understanding and experience. Investigate test procedure and test format from existing test items and test specifications to extract test item correctly. | Provide existing test specification, document and give specific instructions. Confirm mentee’s understanding and output, give feedback. | Jun 2019

## Slide 6: Gap analysis and solution (2/3)
Skill | Gap | Action Item |  | Milestone
 |  | Mentee | Mentor | 
Test Item Execution | Lack of experience in conducting test. | Analyze each test item for better gaining experience. Learn from previous test reports. | Provide materials, instructions. Confirm mentee’s understanding, give feedback. | Jun 2017
Failure Analysis | Lack of experience in using 5why. Lack of knowledge to make a good countermeasure. | Learn from previous issue analysis. Propose or revise solution and make issue report for any problem to supervisor. | Provide specific instructions in each issue case. Confirm mentee’s understanding and output, give feedback. | Jun 2019

## Slide 7: Gap analysis and solution (3/3)
Skill | Gap | Action item |  |  | Milestone
 |  | Mentee |  | Mentor | 
Communication | Lack of experience to make a clear report. | Analyze previous report. Investigate the issue. |  | Share knowledge of complicated issue. Advice mentee, give feedback. | 
Management | Lack of experience in making schedule. |  | Share knowledge how to manage tasks efficiently. Advice mentee, give feedback. |  | 
English |  |  |  |  | 

## Slide 8: Mentor-Mentee interaction
Mentor
Mentee
Provide document, provide input, assign task
Discussion, Review (Email, meeting, direct discussion)
Create/Update Output, Report
Provide output, make report, propose idea

## Slide 9: Training plan
May 2016
May 2018
Jul 2017
Set up environment on e2studio,
CS+, IAR for testing.
Output:
Set up new environment for
simple module with little support or
without support.
Test environment construction
Create test specification on
simple/medium modules of RX,RL78
MCU (DOC, CRC, WDT, POE,
DMAC,R12DA,LVD)
Output:
Test Specification with little
support.
Create test specification on
difficult modules
(MTU,TPU, SCI, S12AD)
Output:
Create test spec with coverage
full of functionality of module
testing.
Test item extraction
1.5
1.5
2
3
Set up environment for different
tools, new device, new IDE.
Output:
Set up new environment for new
device without support

## Slide 10: Training plan
May 2016
May 2018
Jul 2017
Failure analysis
Test execution
Need mentor’s support to find out
root cause and
recurrence prevention for module
issue.
Analyze, find out root cause and
recurrence prevention for
simple/difficult failure
1.5
1.0
2
3
Execute test specification on
simple/medium modules
of RX,RL78 MCU (DOC, CRC,
WDT, POE, DMAC,R12DA,LVD)
Output:
Test result with little support.
Execute test specification on
difficult modules (MTU,TPU, SCI,
S12AD)
Output:
Execute test with ensuring about
the procedures, report clearly, easy understanding

## Slide 11: Training plan
May 2016
May 2018
Jul 2017
Can understand RX, RL78
MCU architecture
-.Support in calculating workload to Develop
process
-Follow the process requirement with
the support of Mentor
-Make project documents for project when
applying development process.
-Follow the process requirement
without the support of Mentor
-Can follow schedule assigned from
leader
-Raise alarm with Mentor’s advice
Can keep schedule and raise alarm if
necessary
2
2
2
1.5
1.5
1.5
Can understand another Renesas
MCU architecture
MCU architecture
Development process
Management ability

## Slide 12: Training plan
May 2016
May 2018
Jul 2017
Create problem report
easy to understand with mentor’s
support.
-Can report problem to leader
-Can report work status in team
2
1.5
Get TOEIC certification 500
Get TOEIC certification 650
Communication ability
English skill

## Slide 13: Commitment
May 2018
Commitment after 2 years:
Achieve the target level 2 for all skills (except Test environment construction and Test execution achieve level 3)
Can do assigned tasks (Verification/Failure analysis) of CG projects without support.
Can support other related projects (PV,FIT Configurator)
Can manage development process for project.

## Slide 14
www.renesas.com
Thank you for your attention